## Introduction
Strategies Timeline, Activities, & Resources (STAR) Log
INTRODUCTION
In the world of changing clinical practice and implementing evidence-based interventions, "if you build it, they will come’ doesn’t work. Individuals and organizations need support and assistance to change. Intervention effectiveness researchers also need to support study sites in implementing the interventions under study. Here are 3 definitions: Implementation strategies are “the stuff we do to help people DO THE THING” (Curran, 2020 [1]; where THE THING is the new intervention). Implementation strategies are “methods or techniques used to enhance the adoption, implementation, and sustainability of a clinical program or practice” (Proctor et al., 2013 [2]). And, "evidence based interventions are the what that is being implemented. Implementation strategies are how we seek to get evidence based interventions into normal practice in clinical or community settings" [3].
A few examples of implementation strategies include training, coaching, audit and feedback, and learning collaboratives. There are several lists of implementation strategies, including Powell et al.'s (2012 [4]) list of 68 strategies in 6 categories. See the article if you'd like more examples.
Implementation strategies must be clearly documented in research studies to enable replication of results and translation of the interventions into practice. Careful documentation is also essential to using information on implementation strategies when analyzing study effects.
The Strategies Timeline, Activities, & Resources (STAR) Log provides a simplified, centralized method for research teams to track implementation strategies.
The STAR Log can be used at any time in your project (e.g., planning, execution). It can be completed and/or updated on a cadence that makes sense for your project (e.g., monthly, quarterly).
The STAR Log is flexible for how you want to track strategies. For example, you can enter one discrete strategy per row (e.g., one training event), or summarize across a series (e.g., the same type of training was delivered monthly for 12 months).
The next tab includes instructions to complete the STAR Log. You can also refer to the Frequently Asked Questions tab, or the Example STAR Log tab that provides a completed log.
[1] Curran G. M. (2020). Implementation science made too simple: a teaching tool. Implementation science communications, 1, 27. https://doi.org/10.1186/s43058-020-00001-z [2] Proctor, E. K., Powell, B. J., & McMillen, J. C. (2013). Implementation strategies: recommendations for specifying and reporting. Implementation science : IS, 8, 139. https://doi.org/10.1186/1748-5908-8-139 [3] https://impsciuw.org/implementation-science/research/implementation-strategies/ [4] Powell, B. J., McMillen, J. C., Proctor, E. K., Carpenter, C. R., Griffey, R. T., Bunger, A. C., Glass, J. E., & York, J. L. (2012). A compilation of strategies for implementing clinical innovations in health and mental health. Medical care research and review : MCRR, 69(2), 123–157. https://doi.org/10.1177/1077558711430690
Authors: Bryan Garner, PhD, The Ohio State University Heather Gotham, PhD, Stanford University School of Medicine Sara Becker, PhD, Northwestern University Hannah Knudsen, PhD, University of Kentucky Todd Molfenter, PhD, University of Wisconsin, Madison Mia Navarro, MS, Stanford University School of Medicine Byron Powell, PhD, Washington University in St. Louis Lisa Saldana, PhD, Chestnut Health Systems - Lighthouse Institute JD Smith, PhD, University of Utah
Funding Statement: This tracking tool was developed by the Implementation Strategies Work Group of the Center for Dissemination and Implementation at Stanford (C-DIAS) and Heal Data2Action Program's (HD2A) Research Adoption Support Center (RASC). Both centers are part of the Center for Dissemination and Implementation at the Stanford University School of Medicine. This work was supported by the NIH National Institute on Drug Abuse through the Helping to End Addiction Long-term® Initiative, or NIH HEAL Initiative® as part of the HEAL Data2Action Program under grant number U2CDA057717, and by the NIH National Institute on Drug Abuse through P50D054072. The content is solely the responsibility of the authors and does not necessarily represent the official views of the National Institutes of Health.
Suggested Citation: Garner, B., Gotham, H., Becker, S., Knudsen, H., Molfenter, T., Navarro, M., Powell, B., Saldana, L., Smith, JD. (2024). Strategies Timeline, Activities, & Resources (STAR) Log. Center for Dissemination and Implementation at Stanford (C-DIAS) and HEAL Data2Action Research Adoption Support Center. www.hd2arasc.org/implementation-guides-and-measures; www.c-dias.org/implementation-guides-and-measures.

## Instructions
Strategies Timeline, Activities, & Resources (STAR) Log
Instructions
Title | Description
Strategy Start Date | Indicate the first day the strategy was initiated.
Strategy End Date | Indicate the day the strategy was completed. If this is an ongoing event, write, “Ongoing”.
Strategy Group | Indicate the type of strategy using Powell et al.'s (2012) 6 categories of strategies: plan, educate, finance, restructure, quality management, and attend to policy context
Strategy Name | Provide a brief name of the strategy. Additional note: We made this a free-response item so one could use a unique strategy name or indicate the ERIC strategy name here. See the FAQ for more information.
What did you do? | Describe the strategy in detail. What did it entail?
Why did you do it? | Describe your rationale for using this strategy. Whose idea was the strategy? What was the reason/source of the strategy?
Who delivered the strategy? | Define who delivered or provided the strategy. Provide official job titles, when available.
How many people delivered the strategy? | Define the number of people involved in delivering the strategy.
On average, how long did it take to prepare and deliver the strategy? | Define the amount of time it took the deliverers to plan and deliver the strategy.
Who received the strategy? | Define the type of individuals receiving the strategy. Write each participant's ID to track individual recipients within one document.
How many people received the strategy? | Define the number of people receiving the strategy.
On average, at what frequency did this strategy occur? | Did this occur once, weekly, monthly, etc.?
On average, how long was each occurrence? | Did each occurrence last 30 minutes, 1 hour, etc.?
What resources or materials were used to deliver the strategy? | Use hyperlinks to attach materials relevant to the strategy (e.g., meeting agendas).
Was the strategy planned or unplanned? | Was this strategy in your original plan or grant application, or was it added at a later point?

## Project Details
Strategies Timeline, Activities, & Resources (STAR) Log
PROJECT DETAILS
Title | Description
Project Name
Intervention Start Date
Date last updated
Person who last updated

## STAR Log Template
STAR Log
TEMPLATE
Strategy Start Date | Strategy End Date | Strategy Group | Strategy Name What do you call this strategy? | What did you do? | Why did you do it? | Who delivered the strategy? | How many people delivered the strategy? | On average, how long did it take to prepare and deliver the strategy? | Who received the strategy? | How many people received the strategy? | On average, at what frequency did this strategy occur? | On average, how long was each occurrence? | What resources or materials were used to deliver the strategy? | Was the strategy planned or unplanned?
Select One
Select One
Select One
Select One
Select One
Select One
Select One
Select One
Select One
Select One
Select One
Select One
Select One
Select One
Select One
Select One
Select One
Select One
Select One
Select One
This sheet should reflect one continuous list of activities and their details. Users can duplicate activities to add (A) more dates of implementation OR (B) different combinations of deliverers/receivers for an strategy.

## Example STAR Log
STAR Log
Example STAR Log
Strategy Start Date | Strategy End Date | Strategy Group | Strategy Name What do you call this strategy? | What did you do? | Why did you do it? | Who delivered the strategy? | How many people delivered the strategy? | On average, how long did it take to prepare and deliver the strategy? | Who received the strategy? | How many people received the strategy? | On average, at what frequency did this strategy occur? | On average, how long was each occurrence? | What resources or materials were used to deliver the strategy? | Was the strategy planned or unplanned?
2022-02-17 | 2022-02-18 | Educate | provider training | 4 hour training on the intervention including didactics, role plays, and Q&A | To teach the providers how to deliver the intervention | PhD level trainers | 2 | 20 hours of prep time to adapt the previously developed content plus 4 hours to deliver | clinic staff including MDs, PAs, APNs, RNs, MAs | 23 | once | 4 hours | link to training curriculum | planned
2022-02-19 | 2022-04-01 | Quality Management | provider audit and feedback | each provider submitted a recording of the intervention with a practice patient. the recording was reviewed by a trainer. then the provider received feedback via conference call. this was done up to 3 times per provider until they achieved competence via a rating scale | To have the providers demonstrate competency in the intervention | PhD level trainers | 2 | Most providers needed to submit 2 practice sessions. Each session takes 90 minutes to code, and then 30 minutes to meet with the provider | only MDs, PAs, and APNs who provided the intervention | 10 | 2 times per person | each provider spent 30 minutes recording themself, and then 30 minutes on a call to get feedback, x two sessions | link to rating scale | planned
2022-03-10 | 2022-03-10 | Plan | Implementation and Sustainment Facilitation (ISF) kickoff meeting | Met with change teams from all 4 clinics to talk about the Implementation and Sustainment Facilitation coaching process | To explain the ISF coaching and how it would work | ISF coach | 1 | 10 hours to prepare materials and 1 hour to deliver | one change team from each clinic, including leadership, providers (MDs, PAs, APNs), staff (RNs, MAs), and administrative personnel | 21 | 1 | 1 hour | link to slides | planned
2022-03-15 | 2022-09-30 | Quality Management | ISF coaching | ISF coach met monthly with each clinic team to provide ISF coaching sessions which included five quality improvement tools preparing champions, assesing readiness and identifying barriers to implementation, and conducting plan-do-study-act cycles | To help the clinics build teams that would be responsible for getting the intervention used in each clinic. | ISF coach | 1 | 6 monthy meetings x 4 clinics x 1 hour of prep x 1 hour of meeting | one change team from each clinic, including leadership, providers (MDs, PAs, APNs), staff (RNs, MAs), and administrative personnel | 21 | monthly | 1 hour | link to ISF trainer tracking form | planned
2022-06-15 | 2022-06-15 | Educate | provider training | 4 hour training on the intervention including didactics, role plays, and Q&A | To teach the providers how to deliver the intervention | PhD level trainers | 2 | 1 hour of prep time to adapt the content from previous training plus 4 hours to deliver | clinic staff including MDs, PAs, APNs, RNs, MAs | 4 | once | 4 hours | link to training curriculum | unplanned
2022-06-20 | 2022-08-13 | Quality Management | provider audit and feedback | each provider submitted a recording of the intervention with a practice patient. the recording was reviewed by a trainer. then the provider received feedback via conference call. this was done up to 3 times per provider until they achieved competence via a rating scale | To have the providers demonstrate competency in the intervention | PhD level trainers | 2 | Most providers needed to submit 2 practice sessions. Each session takes 90 minutes to code, and then 30 minutes to meet with the provider | only MDs, PAs, and APNs who provided the intervention | 3 | 2 times per person | each provider spent 30 minutes recording themself, and then 30 minutes on a call to get feedback, x two sessions | link to rating scale | unplanned
This sheet should reflect one continuous list of activities and their details. Users can duplicate activities to add (A) more dates of implementation OR (B) different combinations of deliverers/receivers for an strategy.

## FAQ
Strategies Timeline, Activities, & Resources (STAR) Log
FREQUENTLY ASKED QUESTIONS
Title | Description
How can we use this tool for planning? | Create one sheet for planned activities and a new sheet for the actual activities implemented.
How can we use this tool with a phased project? | Option 1: Create a new column to indicate the project phase ("Did this strategy occur before or after the intervention started?"). Option 2: Create a new sheet for each project phase ("Pre-Intervention" and "Post-Intervention").
How can we use this tool with a multi-site project? | Option 1: Create a new column to indicate the site ("Site ID"). Option 2: Create a new sheet or Excel file for each project phase (names are site IDs).
How can we use this tool for micro-costing? | Specify the official job titles of deliverers, the time commitments of deliverers, and an itemized list of resources with costs for each strategy. One can use official job titles to search for the national average job salary and impute costs.
Can we use Expert Recommendations for Implementing Change (ERIC) implementation strategy definitions? | Yes! Create a new column to indicate the ERIC strategy definition. You can find the 73 ERIC items here: https://implementationscience.biomedcentral.com/articles/10.1186/s13012-015-0209-1/tables/3
How do we log a repeated strategy that occurred in two different time periods? | Duplicate activities as a new row to add more dates of implementation.
How do we log a repeated strategy with different deliverers or receivers? | Duplicate activities as a new row to add different combinations of deliverers/receivers for an strategy.
How can we document a bundled strategy? | Option 1: Keep the bundled strategy in one row. Use the description to detail all elements of the strategy. Option 2: Break down the bundled strategy elements into separate rows. Indicate in the description that the items are bundled. Note the number of hours should be the same for each row.